## Sheet1
Ragalahari
Description | Assigned To | Action Items
Artists (Anuja) | Anuja
Is the theme decided. |  | Yes- Anuja to get final theme titles from artists
Do we have all the artist names |  | yes. Final few artists names pending. Anuja to get
Do we have all the performances |  | final list of artitsts names including supporting | Event Squence
|  | by Mar 15 | MC- Intro, and light the lamp and Inogural song | 5
Event Timing |  | 2.00pm-5pm | Magical Mandalin- Ketan TamirisaMandolin Solo(5-7min): | 7
Add venue address in the |  | 5-6pm cleaning and return of hall | Gazal Gayaki(45 min): | 45
|  | Anuja to tell artists final performance timings and get | Asha Presentation | 7
|  | agreement. She willl check if local artist can start | Interval | 30
Flyers (Nivedhitha) |  | right after interval by Mar 15. This will save 10min | Classical Dance | 20
Has it been made and completed. | Nivedhitha |  | Setuptime | 10
Has it been printed. Earliest date for printing |  | Still in progreess. Will complete by tonight Mar 17. | Nigtigales of Toledo-Local Toledo Singing Performance | 45
|  | All info for 1st draft provided during meeting | Presentation ceremony | 10
Sponsors (Nivedhitha-Dhathry) |  |  |  | 179
How may sponsors have been contacted |  | Meeting with Nagi on Mar 18th (500-1000$) |  | 2.9833
How much commitment have we received yet |  | By Mar 18 meet at least 3-4 in depts in person
Try to raise $2000-3000 at a minimum by sonsorship
Krishna to help Niveditha with mulitcultural dept & Student union funding proposal
Tickets (Krishna-Sreejit)
Did we buy tickets yet | Krishna | Ganesh to buy tickets and send to Sreejit
Did we start selling it yet | and | Sell tickets every sunday at temple
Did we use online ticketing yet | Sreejit | Sell on Holi event Apr 15
Total Tickets to be sold 267. |  | Sell during Sports event on 26 March
What is the action plan. We have only 1 month |  | Announce during internation dinner
Go door to door to sell to students (Recruit student volunteers to help with this)
Putting flyers up (Sreejit and Krishna) | Krishna | Complete by 3/15/2016
and
Sreejit
Recital Hall (Sreejit)
Did we check out the hall after the booking | Krishna | not yet- will check by 3/18/2016
Did we talk to CPA to provide a person who could manage the sound system and the lights | and | not yet- will check by 3/18/2016
Cost for the person | Sreejit | not yet- will check by 3/18/2016
Get police and cost for that |  | not yet- will check by 3/18/2016
Talk to library to Get Screen and projector to show 5 miin video on Asha Toledo projects before interval |  | Will talk to CPA and see if they have one by 3/18/16
Who is going to present and then show video? |  | Need to decide during next meeting
Who is going to MC on the day of event? |  | Will check if Shimoni will MC or one of our own Asha volunteers wants to do that
Video & Poster & Brochure
Make or stitch Video for presentation |  | Krishna to talk to Sai or Swopnil to make a video with background speech and music
Make poster for each project Snehalaya and Shaaron School and place in the snack area. |  | Ganesh & Pallavi
Who is going to stand by the posters to explain to patrons? |  | Need to decide during next meeting
Who is going to make Brochure with Event info and sponsor info and advertisement? |  | Nivedtha was volunteered (need to confirm)
Food (Dr Varanasi)
Who can we get food from | Dr Varanasi | Suggestions: Bhel Puri, Samosa, Tea Coffee, Mago Shake
Can some restaurant sponsor food, Tandoor or Jewel. Should we get food cheap food from Windsor |  | Need to discuss this further next week when Dr Varanasi and everyone attends the meeting
Insurance (Ganesh) | Ganesh
Need to get coverage from Asha Wide)
Site Visit update for Shaaron School (Ganesh) | Ganesh | Updated the Krihna and Sreejit. Willl provide further update next week. Need to write site visit report
Vote to fund Shaaron School for this year (Ganesh) |  | Will ask for vote next week as there were not enough volunteers by end of meeting