## Sheet1
Action Items |  |  | Minutes of Meetings – Asha Toledo Chapter
Volunteer | Task | Timeline |  | When: Thursday July 9, 2015; 9:00 to 10:00 pm EST
Unmesh | To check with Asha Treasurer on whether we canuse money from Admin account for newletter | 2015-07-12 |  | Attendees: Unmesh Chinte, Ganesh Iyer, Pallavi Iyer, Raj Gosavi, Vikas Ranjan, Anuja Parikh, SK Varanasi, Srikanth Pilla
Administration related points:
| To provide Dr Varanasi Asha's nonprofit number | 2015-07-09
NEW PROJECTS
Ganesh | Send Unmesh Admin account snap shot | 2015-07-09
| Send out timelines and minutes | 2015-07-09 | FUND-RAISING & Publicity
| Talk to Krishnakanth about printing and posting | 2015-07-12 | New Letter changes proposed by team
| Pay for staps if Admin account cannot be used |  | In pie chart change blind, deff to Visually imparired, hearing impaired
Include Snehalaya update provided by Pallavi
Pallavi | Send Anuja newsletter with new inputs | 2015-07-09 | Inclue " Colors of Hope" advertisement
| Provide Snehalay info to Anuja for Newsletter |  | Include new Shaaron school picture
Sreenath | Upload meeting minutes | 2015-07-09 | There will not be any Poem from Pilla
Try to print in A3 and then fold it into 2 or 4 leaves. Anuja will work with Krishna to Figure it out
| Upload newsletter on website,upload picture of new volunteers on website | 2015-07-19 | Vikas suggested that we print address on each news letter and then print
Anuja | Complete newsletter (Pls see suggetion list on side) | 2015-07-12
Major Timelines
| Provide temple address book to Vikas | 2015-07-09 | By Jul 12
Vikas | Convert hard copy of address book to soft copy | 2015-07-10 | Complete converting all address from hard copy to soft copy
| Take final copy of newsletter from Anuja and put addresses on it | 2015-07-12 | Get Admin Account information
Raj | Help Vikas put address on newsletters | 2015-07-12 | Get informatioin about cheaper postage from Toledo post office
Dr. SK | Check with Toledo post office on whether we can print staps for less price | 2015-07-09 | By July 17
Javed | Asha Mailbox in UT | on-going | Get all the address transferred to each and every newsletter
| Manage toledo treasurer email |  | Get proof copy of the newsletter with addresses
By July 19th
Print and post all the news letters
New Voluntter Recruitment
1.. Anuja will active work on getting new volunteers.
2. Dr. Varanasi will work with the new UT students to gauge their interest levels. Once that is determined, a new volunteer will be assigned to shadow existing volunteers
This will enable smooth transfer of responsibilities.