## Sheet1
Action Items |  |  |  | Minutes of Meetings – Asha Toledo Chapter
Volunteer | Task | Timeline | Status | When: March 01, 2015; 3pm-4:30pm EST
Unmesh | Put together a guideline document for project funds disbursement procedure | 2015-03-15 |  | Attendees: Dr. Srikanth Varanasi, Raj Gosavi, Unmesh Chinte, Sreenath Samudrula, Vikas Ranjan, Ganesh Iyer, Pallavi Iyer
Administration related points:
| Work with Sreenath and arrange conf call with Sujit for Arogyaseva project proposal | 2015-03-15 |  | 1. Asha Toledo website:
a. Sreenath has uploaded the Asha Toledo Projects ppt slides to the front page as well as Projects page on the website.
Javed | Asha Mailbox in UT | 2015-03-15 |  | b. Sreenath is working on the new Asha Wide Template and will work on it and have it complete within 2 months. toledo.ashanet.us
Manage toledo treasurer email
Ganesh | Email info about the $50K Award to the grp | 2015-03-04 |  | NEW PROJECTS
| Update Shannon School presentation & upload on google group | 2015-03-04 |  | Three prospective project proposals were discussed for funding.
1. Arogyaseva Phase II: Sujit sent 2 documents to Sreenath and Unmesh regarding proposed funding. Sreenath & Unmesh to work together to
Pallavi | Upload Snehalaya School proposal & related documents on Google drive | 2015-03-04 |  | prepare a few slides on the original project as well as the new proposal request
2. Snehalaya English Medium School - Pallavi presented the Senahalaya English Medium School project and will get more info on past year audit and other financial information
Sreenath | Arrange for Arogyseva site visit for WAH 2014 funds disbursement | 2015-03-15 |  | regarding the school. Also will upload all relevant documents on the ashatoledo google drive.
3. Shaaron School - Ganesh presented Shannon School proposal for teachers salary.
| Create another google group for past ASHA volunteers & other interested community members | 2015-03-15 |  | Information on all the 3 projects will be shared through google drive with all the core volunteers and voting will be done on which projects
to take up & how much $$ to assign for each project
| Upload meeting minutes | 2015-03-03
Vikas | Compile ashatoledo emails and summarize important highlights | 2015-03-15 |  | Other Topics
Raj | Complete Arogyaseva project report for Asha Wide | 2015-03-05 |  | 1. Asha Toledo Chapter registration with UT
Dr. SK | Email contact info of new student volunteers to Ganesh, invite them to next meeting | 2015-03-03 |  | a. Javed to go and check at the Student Union if there is an existing Asha Toledo mailbox.
Ginni | New point of contact for UT | On-going |  | b. The Chapter is registered until August 2015. Re-register in August for next year
Anuja | New volunteer recruitment | On-going |  | c. Try to include Ginni as the point of contact moving forward
NEXT MEETING ON MARCH 15, 2015 @ 3PM
2. Ganesh will find more information on the $50K Award from UK for good philanthropic work done by an organization/individual.
If possible, then a team of volunteers will work to put a proposal together within the April 01 deadline.